## Test schedule
Palomar LGSAO test schedule | [10 empty] | v1.1: 01/03/07 - AB
4-6 January 2007 (local) | [10 empty] | Spotters requested 20:00-06:00 (on station 20:30-05:45)
Test ID | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description | Priority | Duration | Lead | Clear sky | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2007-01-04 |  |  |  | 17:01 | 17:51 | 7:11 | 5:54 | 6:44
| 10:00 | 12:00 |  | Install LLT |  |  |  |  | closed | zen |  | 1 | 2 | MD | N | N
| 12:00 | 13:00 |  | Cable AO system |  |  |  |  | closed | zen |  | 1 | 1 | MD | N | N
1 | 12:00 | 16:00 |  | BTO/LLT alignment and checkout |  |  |  |  | closed | zen | Cannot align LLT until AO control established. | 1 | 4 | AB | N | N
2 | 13:00 | 16:00 |  | AO bench setup and checkout |  |  |  |  | closed | zen | Switch dichroic, co-focus WFS, setup chopper & delay generator. | 1 | 3 | JR | N | N
| 14:00 | 14:30 |  | status and safety meeting | [8 empty] | 0.5
3 | 16:00 | 16:30 |  | Align laser to BTO |  |  |  |  | closed | NA | Align CSFL to BTO in Coude lab. | 1 | 0.5 | AB | N | N
4 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | JC
5 | 16:00 | 17:30 |  | Calibrate PHARO |  |  |  |  | closed | zen | Focus PHARO, check pupil alignment, calibrate centroid offsets. | 1 | 1.5 | JH
6 | 16:30 | 17:30 |  | Test-fire laser in dome. |  |  |  |  | closed | zen | Verify BTO alignment & Q3 interlock. Measure transmission. | 1 | 1 | AB | N | Y
| 17:00 | 18:00 |  | dinner | [8 empty] | 1
7 | 17:30 | 18:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 2 | 0.5 | JH | N | N
8 | 18:00 | 19:30 |  | LLT boresighting |  |  |  |  | NGS | V=3 | Check and correct LLT boresighting. | 1 | 1.5 | HP | N | N
9 | 19:30 | 21:30 |  | LLT image quality |  |  |  |  | NGS | V=3 | Optimize LLT image quality. | 2 | 2 | AM | N | N
10 | 21:30 | 22:30 |  | LGS characterization |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | MT | Y | Y
11 | 22:30 | 24:30 |  | LGS bright star performance |  |  |  |  | LGS | V=10 | Acquire star, optimize servo loops, measure Strehl & PSD | 1 | 2 | MT | Y | Y
12 | 24:30 | 28:30 |  | LGS science demo |  |  |  |  | LGS | V=15 | Observe 2 science targets | 1 | 4 | AB | Y | Y
13 | 28:30 | 30:00 |  | Off-axis acquisition procedure |  |  |  |  | LGS | V=10 | Demonstrate off-axis NGS acquisition procedure | 2 | 1.5 | AB | N | Y
2007-01-05 |  |  |  | 17:02 | 17:52 | 7:15 | 5:54 | 6:44
| 10:00 | 16:00 |  | daytime contingency |  |  |  |  | closed |  | Possible COO all-hands meeting at 13:00. |  | 6 |  | N
| 14:00 | 14:30 |  | status and safety meeting | [8 empty] | 0.5
1 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | JC
2 | 16:30 | 17:00 |  | Test-fire laser in dome. |  |  |  |  | closed | zen | Verify BTO alignment & Q3 interlock. | 1 | 0.5 | AB | N | Y
| 17:00 | 18:00 |  | dinner | [8 empty] | 1
3 | 17:30 | 18:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 2 | 0.5 | JH | N | N
4 | 18:00 | 20:30 |  | NGS low-light tests |  |  |  |  | NGS | V=15 | Compare low-light centroid algorithms and reconstructors. | 2 | 2.5 | CS | Y | N
5 | 20:30 | 21:30 |  | LGS characterization |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | MT | Y | Y
6 | 21:30 | 22:30 |  | LGS bright star performance |  |  |  |  | LGS | V=10 | Acquire star, optimize servo loops, measure Strehl & PSD | 1 | 1 | MT | Y | Y
7 | 22:30 | 25:30 |  | LGS faint star performance |  |  |  |  | LGS | V=17 | Optimize TT, measure Strehl & PSD for V=14,15,16,17 | 2 | 3 | JR | Y | Y
8 | 25:30 | 26:30 |  | Rayleigh scatter characterization |  |  |  |  | LGS | zen | Quantify altitude of scattering components on WFS. | 3 | 1 | AB | Y | Y
9 | 26:30 | 28:30 |  | LGS science demo |  |  |  |  | LGS | V=15 | Observe 1 science target | 3 | 2 | AB | Y | Y
| 28:30 | 29:30 |  | LGS contingency |  |  |  |  | LGS |  |  | 3 | 1 |  |  | Y
2007-01-06 |  |  |  | 17:02 | 17:52 | 7:19 | 5:54 | 6:44
| 10:00 | 16:00 |  | daytime contingency |  |  |  |  | closed |  |  |  | 6 |  | N
| 14:00 | 14:30 |  | status and safety meeting | [8 empty] | 0.5
1 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | JC
2 | 16:30 | 17:00 |  | Test-fire laser in dome. |  |  |  |  | closed | zen | Verify BTO alignment & Q3 interlock. | 1 | 0.5 | AB | N | Y
| 17:00 | 18:00 |  | dinner | [8 empty] | 1
3 | 17:30 | 18:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 2 | 0.5 | JH | N | N
4 | 18:00 | 20:30 |  | NGS contingency |  |  |  |  | NGS |  |  |  | 2.5 |  |  | N
5 | 20:30 | 21:30 |  | LGS characterization |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | MT | Y | Y
| 21:30 | 29:45 |  | LGS contingency |  |  |  |  | LGS |  |  | 3 | 8.25 |  |  | Y
Proposed LGS experiments
1 | 0:00 | 1:00 |  | UTT performance |  |  |  |  | LGS | zen | Investigate UTT performance (ideas, anyone?) | 3 | 1 | MT | Y | Y
2 | 1:00 | 3:00 |  | LGS performance vs. airmass |  |  |  |  | LGS | V=10 | Measure laser magnitude & Strehl at el=90,60,45 | 3 | 2 | AB | Y | Y
3 | 3:00 | 5:00 |  | LGS isoplanatism |  |  |  |  | LGS | V=10 | Measure LGS and NGS isoplanatic angles | 3 | 2 | AB | Y | Y
Proposed NGS experiments
1 | 0:00 | 2:00 |  | LOWFS flexure |  |  |  |  | NGS | V=4 | Good cloudy night test | 1 | 2 | MT | N | N
2 | 2:00 | 5:00 |  | LOWFS performance |  |  |  |  | NGS | V=16 | continue LOWFS performance test from Sep. run | 2 | 3 | JR | Y | N
3 | 5:00 | 6:00 |  | LOWFS focus performance |  |  |  |  | NGS | V=17 | Measure LOWFS focus in dual NGS mode | 3 | 1 | AB | N | N
Proposed closed-dome experments
1 | 0:00 | 2:00 |  | LOWFS flexure |  |  |  |  | WL | move | Measure flexure of LOWFS using white light stimulus. | 1 | 2 | MT | N | N
2 | 2:00 | 4:00 |  | Recalibrate BTO model | [5 empty] | move | Extend current model to higher airmass. | 1 | 2 | AB | N | 660
3 | 4:00 | 6:00 |  | Field-dependent LOWFS focus |  |  |  |  | WL | zen |  | 1 | 2 | JR | N | N
Background experiments
1 |  |  |  | Aircraft camera sensitivity |  |  |  |  | NGS |  | Gather statistics on camera vs. spotter aircraft sensitivity | 2 |  | JC | N | N
1 |  |  |  | RADAR sensitivity |  |  |  |  | NGS |  | Note range and SNR of all RADAR aircraft detections | 3 |  | JC | N | N
2 |  |  |  | Laser diagnostics benches |  |  |  |  | LGS |  | Calibrate output of photodiodes & cameras. | 2 |  | AM | N | Y