## Test schedule
Palomar LGSAO test schedule | [10 empty] | v1.1: 02/23/07 - AB&JR
26-28 February 2007 (local) | [10 empty] | Spotters requested 19:30-05:30 (on station 20:00-05:30)
Test ID | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description | Priority | Duration | Lead | Clear sky | r0>10cm | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2007-02-26 |  |  |  | 17:48 | 18:35 | 10:40 | 5:26 | 6:12
1 | 10:00 | 13:00 |  | Install LLT |  |  |  |  | closed | zen |  | 1 | 3 | Doyle | N | N | N
2 | 10:00 | 14:00 |  | LGS computer setup and testing |  |  |  |  | closed | NA | Set up computer, test temperature control. | 1 | 4 | Guiwits | N | N | N
3 | 10:00 | 14:00 |  | AO bench setup and checkout |  |  |  |  | closed | zen | Switch dichroic, co-focus WFS, setup chopper & delay generator. | 1 | 4 | Roberts | N | N | N
4 | 13:00 | 14:00 |  | BTO setup and checkout |  |  |  |  | closed | zen | Test Q3, servo control. | 1 | 1 | Angione | N | N | 660
| 14:00 | 14:30 |  | status and safety meeting | [8 empty] | 0.5
5 | 14:30 | 15:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 1 | Tripathi | N | N | N
6 | 14:30 | 16:00 |  | LLT alignment and checkout |  |  |  |  | closed | zen | Align stimulus laser to LLT. | 1 | 1.5 | Bouchez | N | N | 660
7 | 15:30 | 16:00 |  | Align laser to BTO |  |  |  |  | closed | NA | Align CSFL to BTO in Coude lab. | 1 | 0.5 | Bouchez | N | N | N
8 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
9 | 16:30 | 17:30 |  | Laser alignment in dome. |  |  |  |  | closed | zen | Low/high power laser projection in the dome. | 1 | 1 | Bouchez | N | N | N
10 | 16:00 | 17:00 |  | Calibrate PHARO |  |  |  |  | closed | NA | Focus PHARO, check pupil alignment, calibrate centroid offsets. | 1 | 1 | Burruss
| 17:30 | 18:30 |  | dinner | [8 empty] | 1
11 | 18:15 | 18:45 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 2 | 0.5 | Burruss | N | N | N
12 | 18:45 | 20:30 |  | LLT boresighting |  |  |  |  | NGS | V=3 | Check and correct LLT boresighting. | 1 | 1.75 | Moore | N | N | N
13 | 20:30 | 21:30 |  | LLT image quality |  |  |  |  | NGS | V=3 | Optimize LLT image quality. | 2 | 1 | Roberts | N | N | N
14 | 21:30 | 22:30 |  | LGS acquisition and char. |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | Troy | Y | N | Y
15 | 22:30 | 23:30 |  | Test laser frequency lock |  |  |  |  | LGS | zen | Test effects of etalon dither on HOWFS return. | 2 | 1 | Bouchez | Y | N | Y
16 | 23:30 | 24:30 |  | Circular polarization experiment |  |  |  |  | LGS | zen | Repeat Jul. 06 experiment. Requires person at prime focus. | 2 | 1 | Bouchez | Y | N | Y
17 | 24:30 | 26:30 |  | LGS bright star performance |  |  |  |  | LGS | V=10 | Acquire star, optimize servo loops, measure Strehl & PSD | 1 | 2 | Roberts | Y | Y | Y
18 | 26:30 | 29:30 |  | LGS science demo |  |  |  |  | LGS | V=15 | Observe 2 science targets | 1 | 3 | Bouchez | Y | Y | Y
2007-02-27 |  |  |  | 17:49 | 18:36 | 10:44 | 5:24 | 6:11
| 14:00 | 14:30 |  | status and safety meeting | [8 empty] | 0.5
1 | 14:30 | 15:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 1 | Tripathi | N | N | N
2 | 15:30 | 16:00 |  | Align laser to BTO |  |  |  |  | closed | NA | Align CSFL to BTO in Coude lab. | 1 | 0.5 | Bouchez | N | N | N
3 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
4 | 16:30 | 17:30 |  | Test-fire laser in dome. |  |  |  |  | closed | zen | Verify BTO alignment & Q3 interlock. | 1 | 1 | Bouchez | N | N | Y
| 17:30 | 18:30 |  | dinner | [8 empty] | 1
5 | 18:15 | 18:45 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 2 | 0.5 | Burruss | N | N | N
2007-02-28 |  |  |  | 17:50 | 18:37 | 10:48 | 5:23 | 6:10
| 14:00 | 14:30 |  | status and safety meeting | [8 empty] | 0.5
1 | 14:30 | 15:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 1 | Tripathi | N | N | N
2 | 15:30 | 16:00 |  | Align laser to BTO |  |  |  |  | closed | NA | Align CSFL to BTO in Coude lab. | 1 | 0.5 | Bouchez | N | N | N
3 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
4 | 16:30 | 17:30 |  | Test-fire laser in dome. |  |  |  |  | closed | zen | Verify BTO alignment & Q3 interlock. | 1 | 1 | Bouchez | N | N | Y
| 17:30 | 18:30 |  | dinner | [8 empty] | 1
5 | 18:15 | 18:45 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 2 | 0.5 | Burruss | N | N | N
Proposed LGS experiments
1 | 0:00 | 1:00 |  | LGS bright star performance |  |  |  |  | LGS | V=10 | Acquire star, optimize servo loops, measure Strehl & PSD | 1 | 1 | Roberts | Y | Y | Y
2 | 1:00 | 4:00 |  | LGS faint star performance |  |  |  |  | LGS | V=17 | Optimize TT, measure Strehl & PSD for V=14,15,16,17 | 2 | 3 | Roberts | Y | Y | Y
3 | 4:00 | 5:00 |  | Rayleigh scatter characterization |  |  |  |  | LGS | zen | Quantify altitude of scattering components on WFS. | 3 | 1 | Bouchez | Y | N | Y
4 | 5:00 | 6:30 |  | Off-axis acquisition procedure |  |  |  |  | LGS | V=10 | Demonstrate off-axis NGS acquisition procedure | 2 | 1.5 | Bouchez | N | N | Y
5 | 6:30 | 7:30 |  | UTT performance |  |  |  |  | LGS | zen | Investigate UTT performance. GOOD. | 3 | 1 | ? | Y | Y | Y
6 | 7:30 | 9:30 |  | LGS performance vs. airmass |  |  |  |  | LGS | V=10 | Measure laser magnitude & Strehl at el=90,60,45 | 3 | 2 | ? | Y | Y | Y
7 | 9:30 | 11:30 |  | LGS isoplanatism |  |  |  |  | LGS | V=10 | Measure LGS and NGS isoplanatic angles | 3 | 2 | AB | Y | Y | Y
Proposed NGS experiments
1 | 0:00 | 2:00 |  | Demo flexure compensation. |  |  |  |  | NGS | V=4 | Good cloudy night test. | 1 | 2 | Bouchez | N | N | N
2 | 2:00 | 4:00 |  | Leaky intergrator testing |  |  |  |  | NGS | V=4 | Requires stable seeing, clear sky. | 1 | 2 | Troy | N | N | N
3 | 4:00 | 7:00 |  | Faint object NGS testing |  |  |  |  | NGS | V=15 | Need a clear test plan. | 1 | 3 | Shelton | N | N | N
4 | 7:00 | 10:00 |  | LOWFS performance |  |  |  |  | NGS | V=16 | Continue LOWFS performance test from Sep. run | 2 | 3 | Roberts | Y | Y | N
Proposed closed-dome experments
1 | 0:00 | 2:00 |  | Adjust PF diagnostics bench filters |  |  |  |  | NA | zen | Using high-power laser in dome. | 1 | 2 | Moore | N | N | Y
2 | 2:00 | 5:00 |  | Recalibrate BTO model |  |  |  |  | LGS | move | Extend current model to higher airmass. | 1 | 3 | Bouchez | N | N | 660
3 | 5:00 | 7:00 |  | Demo flexure compensation. |  |  |  |  | WL | move | Measure flexure of LOWFS using white light stimulus. | 2 | 2 | Bouchez | N | N | N
4 | 7:00 | 9:00 |  | Measure LOWFS flexure |  |  |  |  | WL | move | Re-measure LOWFS flexure to verify repeatability. | 2 | 2 | Bouchez | N | N | N
5 | 9:00 | 11:00 |  | AO software debugging and testing |  |  |  |  | NA | NA | Debug BTO logging, others… | 3 | 2 | Angione | N | N | N
6 | 11:00 | 13:00 |  | Field-dependent LOWFS focus |  |  |  |  | WL | zen | Does not take into account telescope field curvature. | 3 | 2 | Roberts | N | N | N
Background experiments
1 |  |  |  | Aircraft camera sensitivity |  |  |  |  | NGS |  | Gather statistics on camera vs. spotter aircraft sensitivity | 2 |  | Cromer | Y | N | N
2 |  |  |  | RADAR sensitivity |  |  |  |  | NGS |  | Note range and SNR of all RADAR aircraft detections | 3 |  | Cromer | N | N | N
3 |  |  |  | Laser diagnostics benches |  |  |  |  | LGS |  | Calibrate output of photodiodes & cameras. | 2 |  | Moore | N | N | Y
4 |  |  |  | Understand IRCAM latency |  |  |  |  | LGS |  |  | 2 |  | Cromer | N | N | N