## Test schedule
Palomar LGSAO test schedule | [10 empty] | v1.1: 04/18/07 - AB & JR
23-27 March 2007 (local) | [10 empty] | Spotters requested 19:55-05:15 (on station 20:25-05:05)
Test ID | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description | Priority | Duration | Lead | Clear sky | r0>10cm | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2007-04-23 |  |  |  | 19:31 | 20:20 | 14:20 | 5:11 | 6:00
1 | 10:00 | 13:00 |  | Install LLT |  |  |  |  | closed | zen |  | 1 | 3 | Doyle | N | N | N
2 | 10:00 | 14:00 |  | AO bench setup and checkout |  |  |  |  | closed | zen | Check Aerotech controller, co-focus WFSs, setup chopper & delay generator. | 1 | 4 | Roberts | N | N | N
3 | 13:00 | 13:30 |  | BTO setup and checkout |  |  |  |  | closed | zen | Test Q3, servo control. | 1 | 0.5 | Angione | N | N | 660
4 | 13:30 | 15:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 2 | Tripathi | N | N | N
5 | 13:30 | 15:30 |  | LLT alignment and checkout |  |  |  |  | closed | zen | Align stimulus laser to LLT. | 1 | 2 | Moore | N | N | 660
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
6 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
7 | 16:30 | 17:30 |  | Verify BTO alignment |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | N
8 | 18:00 | 19:00 |  | Calibrate PHARO |  |  |  |  | closed | NA | Calibrate centroids for both refl. spot & dichroic. | 1 | 1 | Hickey
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
9 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
10 | 20:30 | 21:00 |  | NGS science |  |  |  |  | NGS | V=8 | Mike Werner target | 1 | 0.5 | Bouchez | N | N | N
11 | 21:00 | 22:00 |  | LLT boresighting |  |  |  |  | LGS | zen | Project laser at zenith; Check and optimize boresighting. | 1 | 1 | Moore | N | N | Y
12 | 22:00 | 23:00 |  | LLT image quality |  |  |  |  | LGS | zen | Optimize LGS spot size by translating LLT secondary. | 2 | 1 | Petrie | N | N | Y
13 | 23:00 | 23:30 |  | LGS zenith optimization |  |  |  |  | LGS | zen | Complete LGS acquisition & zenith optimization test plans | 1 | 0.5 | Roberts | N | N | Y
14 | 23:30 | 24:30 |  | LGS bright star optimization |  |  |  |  | LGS | V=10 | Acquire star, optimize servo loops, measure Strehl | 1 | 1 | Roberts | Y | Y | Y
15 | 24:30 | 25:30 |  | UTT vs. CR angle |  |  |  |  | LGS | zen | Test new reconstructor software | 2 | 1 | Bouchez | N | N | Y
16 | 25:30 | 28:30 |  | LGS science demo |  |  |  |  | LGS | V=15 | Observe 2 science targets and test PHARO scripts | 2 | 3 | Bouchez | Y | Y | Y
17 | 28:30 | 29:00 |  | LGS contingency |  |  |  |  | LGS |  |  | 2 | 0.5 |  |  |  | Y
18 | 29:00 | 29:45 |  | Field dependent LOWFS focus |  |  |  |  | NGS | V=10 | Acquire star at several points in LOWFS patrol field, record focus. | 2 | 0.75 | Bouchez | N | N | N
2007-04-24 |  |  |  | 19:32 | 20:21 | 14:24 | 5:10 | 5:59
1 | 10:00 | 14:00 |  | AO bench setup and checkout |  |  |  |  | closed | zen | Check chopper control | 1 | 4 | Roberts | N | N | N
2 | 14:30 | 15:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 1 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
3 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
4 | 16:30 | 17:30 |  | Verify BTO alignment |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | N
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
5 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
6 | 20:30 | 21:15 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, UTT optimization | 1 | 0.75 | Troy | Y | N | Y
7 | 21:15 | 25:15 |  | LGS faint target performance |  |  |  |  | LGS | V=17 | Acquire and optimize for 2 stars each at V=14,15,16,17 | 1 | 4 | Roberts | Y | Y | Y
8 | 25:15 | 28:15 |  | LGS science demo |  |  |  |  | LGS | V=15 | Observe 2 science targets and test PHARO scripts | 2 | 3 | Bouchez | Y | Y | Y
9 | 28:15 | 29:00 |  | Circular polarization experiment |  |  |  |  | LGS | zen | Repeat Jul. 06 experiment. Requires person at prime focus. | 3 | 0.75 | Bouchez | Y | N | Y
10 | 29:00 | 29:30 |  | LOWFS transfer curves |  |  |  |  | NGS | V=10 | Measure Focus transfer curves | 3 | 0.5 | Roberts | N | N | N
2007-04-25 |  |  |  | 19:32 | 20:22 | 14:28 | 5:08 | 5:58
1 | 14:30 | 15:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 1 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
2 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
3 | 16:30 | 17:30 |  | Verify BTO alignment |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | N
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
4 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 2 | 0.5 | Burruss | N | N | N
5 | 20:30 | 21:15 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, UTT optimization | 1 | 0.75 | Bouchez | Y | N | Y
6 | 21:15 | 29:00 |  | Shared-risk Science |  |  |  |  | LGS | V=17 | LGS-AO Multiplicity and Planet Formation at Bottom of IMF | 1 | 7.75 | Surace | Y | N | Y
2007-04-26 |  |  |  | 19:33 | 20:23 | 14:32 | 5:07 | 5:57
1 | 14:30 | 15:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 1 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
2 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
3 | 16:30 | 17:30 |  | Verify BTO alignment |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | N
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
4 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
5 | 20:30 | 21:15 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, UTT optimization | 1 | 0.75 | Troy | Y | N | Y
6 | 21:15 | 29:00 |  | Shared-risk Science |  |  |  |  | LGS | V=17 | LGS-AO Multiplicity and Planet Formation at Bottom of IMF | 1 | 7.75 | Lowrance | Y | N | Y
2007-04-27 |  |  |  | 19:34 | 20:24 | 14:36 | 5:06 | 5:56
1 | 14:30 | 15:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 1 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
2 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
3 | 16:30 | 17:30 |  | Verify BTO alignment |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | N
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
4 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Burruss | N | N | N
5 | 20:30 | 21:15 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, UTT optimization | 1 | 0.75 | Troy | Y | N | Y
6 | 21:15 | 29:00 |  | Shared-risk Science |  |  |  |  | LGS | V=17 | LGS-AO Observations of Ultraluminous IR Galaxies | 1 | 7.75 | Lowrance | Y | N | Y
Other proposed LGS experiments
1 | 0:00 | 1:00 |  | LGS bright star performance |  |  |  |  | LGS | V=10 | Acquire star, optimize servo loops, measure Strehl & PSD | 1 | 1 | Roberts | Y | Y | Y
2 | 1:00 | 4:00 |  | LGS faint star performance |  |  |  |  | LGS | V=17 | Optimize TT, measure Strehl & PSD for V=14,15,16,17 | 2 | 3 | Roberts | Y | Y | Y
3 | 4:00 | 5:00 |  | Rayleigh scatter characterization |  |  |  |  | LGS | zen | Quantify altitude of scattering components on WFS. | 3 | 1 | Bouchez | Y | N | Y
4 | 5:00 | 6:30 |  | Off-axis acquisition procedure |  |  |  |  | LGS | V=10 | Demonstrate off-axis NGS acquisition procedure | 2 | 1.5 | Bouchez | N | N | Y
5 | 6:30 | 7:30 |  | UTT performance |  |  |  |  | LGS | zen | Investigate UTT performance. GOOD. | 3 | 1 | ? | Y | Y | Y
6 | 7:30 | 9:30 |  | LGS performance vs. airmass |  |  |  |  | LGS | V=10 | Measure laser magnitude & Strehl at el=90,60,45 | 3 | 2 | ? | Y | Y | Y
7 | 9:30 | 11:30 |  | LGS isoplanatism |  |  |  |  | LGS | V=10 | Measure LGS and NGS isoplanatic angles | 3 | 2 | AB | Y | Y | Y
8 | 11:30 | 12:30 |  | Test laser frequency lock |  |  |  |  | LGS | zen | Test effects of etalon dither on HOWFS return. | 2 | 1 | Bouchez | Y | N | Y
Other proposed NGS experiments
1 | 0:00 | 0:30 |  | Field dependent LOWFS focus |  |  |  |  | NGS | V=10 | Acquire star at several points in LOWFS patrol field, record focus. | 2 | 0.5 | Bouchez | N | N | N
2 | 0:30 | 1:30 |  | LOWFS transfer curves |  |  |  |  | NGS | V=10 | Measure TT and Focus transfer curves | 3 | 1 | Roberts | N | N | N
3 | 1:30 | 3:30 |  | Demo flexure compensation. |  |  |  |  | NGS | V=4 | Good cloudy night test. | 1 | 2 | Bouchez | N | N | N
4 | 3:30 | 5:30 |  | Leaky intergrator testing |  |  |  |  | NGS | V=4 | Requires stable seeing, clear sky. | 1 | 2 | Troy | N | N | N
5 | 5:30 | 8:30 |  | Faint object NGS testing |  |  |  |  | NGS | V=15 | Need a clear test plan. | 1 | 3 | Shelton | N | N | N
6 | 8:30 | 11:30 |  | LOWFS performance |  |  |  |  | NGS | V=16 | Continue LOWFS performance test from Sep. run | 2 | 3 | Roberts | Y | Y | N
Proposed closed-dome experments
1 | 0:00 | 2:00 |  | Adjust PF diagnostics bench filters |  |  |  |  | NA | zen | Using high-power laser in dome. | 1 | 2 | Moore | N | N | Y
2 | 2:00 | 4:00 |  | Demo flexure compensation. |  |  |  |  | WL | move | Measure flexure of LOWFS using white light stimulus. | 2 | 2 | Bouchez | N | N | N
3 | 4:00 | 6:00 |  | Measure LGS NCP flexure |  |  |  |  | WL | move | Re-measure flexure while locked on LOWFS. | 2 | 2 | Bouchez | N | N | N
4 | 6:00 | 8:00 |  | Measure NGS NCP flexure |  |  |  |  | WL | move | Measure flexure while locked on HOWFS. | 2 | 2 | Bouchez | N | N | N
5 | 8:00 | 10:00 |  | Field-dependent LOWFS focus |  |  |  |  | WL | zen | Does not take into account telescope field curvature. | 3 | 2 | Roberts | N | N | N
Background experiments
1 |  |  |  | Aircraft camera sensitivity |  |  |  |  | NGS |  | Gather statistics on camera vs. spotter aircraft sensitivity | 2 |  | Cromer | Y | N | N
2 |  |  |  | RADAR sensitivity |  |  |  |  | NGS |  | Note range and SNR of all RADAR aircraft detections | 3 |  | Cromer | N | N | N
3 |  |  |  | Laser diagnostics benches |  |  |  |  | LGS |  | Calibrate output of photodiodes & cameras. | 2 |  | Moore | N | N | Y
4 |  |  |  | Understand IRCAM latency |  |  |  |  | LGS |  |  | 2 |  | Cromer | N | N | N