## Test schedule
Palomar LGSAO test schedule | [10 empty] | v1.1: 05/21/07 - AB & JR
23-26 May 2007 (local) | [10 empty] | Spotters requested 20:15-04:45 PDT (on station 20:55-04:35)
Test ID | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description | Priority | Duration | Lead | Clear sky | r0>10cm | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2007-05-23 |  |  |  | 19:54 | 20:47 | 16:19 | 4:41 | 5:34
1 | 9:00 | 12:00 |  | Install AO |  |  |  |  | closed | zen |  | 1 | 3 | Sweet | N | N | N
2 | 12:00 | 14:00 |  | Install LLT |  |  |  |  | closed | zen |  | 1 | 2 | Sweet | N | N | N
3 | 12:00 | 16:00 |  | AO bench setup and checkout |  |  |  |  | closed | zen | Check Aerotech controller, co-focus WFSs, setup chopper & delay generator. | 1 | 4 | Roberts | N | N | N
4 | 14:00 | 15:00 |  | BTO setup |  |  |  |  | closed | zen | Setup hardware & softeware, check servo control. | 1 | 1 | Bouchez | N | N | 660
5 | 15:00 | 17:00 |  | LLT alignment and checkout |  |  |  |  | closed | zen | Align stimulus laser to LLT. Requires 2 personnel at PF. | 1 | 2 | Petrie | N | N | 660
6 | 14:00 | 17:00 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 3 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
7 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
8 | 16:30 | 17:30 |  | Verify BTO alignment |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
9 | 18:30 | 19:30 |  | Calibrate PHARO |  |  |  |  | closed | NA | Calibrate centroids for both refl. spot & dichroic. | 1 | 1 | Burruss
| 18:30 | 19:30 |  | dinner | [8 empty] | 1
10 | 20:15 | 20:45 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Burruss | N | N | N
11 | 20:45 | 21:45 |  | LLT boresighting |  |  |  |  | LGS | zen | Project at zenith; Check boresighting, align finderscope on star | 1 | 1 | Bouchez | N | N | Y
12 | 21:45 | 23:15 |  | LLT image quality |  |  |  |  | LGS | zen | Optimize LGS spot size by translating LLT secondary. | 2 | 1.5 | Petrie | N | N | Y
13 | 23:15 | 23:45 |  | LGS zenith optimization |  |  |  |  | LGS | zen | Complete LGS acquisition & zenith optimization test plans | 1 | 0.5 | Roberts | N | N | Y
14 | 23:45 | 24:45 |  | Circular polarization experiment |  |  |  |  | LGS | zen | Repeat Jul. 06 experiment. Requires person at prime focus. | 2 | 1 | Bouchez | Y | N | Y
15 | 24:45 | 26:45 |  | LGS HO aberrations |  |  |  |  | LGS | V=10 | Check HO performance on PHARO, on extended NGS (Neptune) | 1 | 2 | Roberts | Y | Y | Y
16 | 26:45 | 28:45 |  | LGS LO performance |  |  |  |  | LGS | V=16 | Follow full TT optimization test plan for V=16, 17 stars. | 1 | 2 | Roberts | Y | Y | Y
17 | 28:45 | 29:15 |  | AO f-ratio tests |  |  |  |  | NGS | V=6 | Measure platscale at LOWFS focus on binary | 1 | 0.5 | Bouchez | N | N | N
2007-05-24 |  |  |  | 19:54 | 20:48 | 16:23 | 4:40 | 5:34
1 | 12:00 | 16:00 |  | AO bench setup and checkout |  |  |  |  | closed | zen | Take data for summer student (telescope moves required) | 1 | 4 | Roberts | N | N | N
2 | 14:00 | 17:00 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 3 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
3 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
4 | 16:30 | 17:30 |  | Verify BTO alignment |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | N
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
5 | 20:15 | 20:45 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
6 | 20:45 | 21:45 |  | Test LLT Pulnix |  |  |  |  | NGS | V=3 |  | 1 | 1 | Moore | N | N | N
7 | 21:45 | 22:15 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus | 1 | 0.5 | Troy | Y | N | Y
8 | 22:15 | 22:45 |  | LGS bright star optimization |  |  |  |  | LGS | V=10 | Optimize and measure Strehl | 1 | 0.5 | Bouchez | Y | N | Y
8 | 22:15 | 28:15 |  | LGS science demo |  |  |  |  | LGS | V=15 | Observe 3 science targets and test PHARO scripts | 2 | 6 | Bouchez | Y | Y | Y
2007-05-25 |  |  |  | 19:55 | 20:49 | 16:27 | 4:39 | 5:33
1 | 14:30 | 15:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 1 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
2 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
3 | 16:30 | 17:30 |  | Verify BTO alignment |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | N
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
4 | 20:15 | 20:45 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 2 | 0.5 | Burruss | N | N | N
5 | 20:45 | 21:30 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, UTT optimization | 1 | 0.75 | Bouchez | Y | N | Y
6 | 21:30 | 28:30 |  | Shared-risk Science |  |  |  |  | LGS | V=17 | LGS-AO Multiplicity and Planet Formation at Bottom of IMF | 1 | 7 | Beichman | Y | N | Y
2007-05-26 |  |  |  | 19:56 | 20:50 | 16:31 | 4:39 | 5:33
1 | 14:30 | 15:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final alignment and testing of laser, control loops. | 1 | 1 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
2 | 16:00 | 16:30 |  | Test safety interlocks |  |  |  |  | closed | NA | Install barriers and test interlocks. | 1 | 0.5 | Cromer
3 | 16:30 | 17:30 |  | Verify BTO alignment |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | N
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
4 | 20:15 | 20:45 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
5 | 20:45 | 21:30 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, UTT optimization | 1 | 0.75 | Troy | Y | N | Y
6 | 21:30 | 28:30 |  | Shared-risk Science |  |  |  |  | LGS | V=17 | LGS-AO Multiplicity and Planet Formation at Bottom of IMF | 1 | 7 | Beichman | Y | N | Y