## Test schedule
Palomar LGSAO test schedule | [10 empty] | v1.0: 07/18/07 - AB & JR
23-28 July 2007 (local) | [10 empty] | Spotters requested 20:15 - 05:00 PDT (on station 20:55 - 04:50)
Test ID | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description | Priority | Duration | Lead | Clear sky | r0>10cm | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2007-07-23 |  |  |  | 20:02 | 20:56 | 20:19 | 4:53 | 5:46
1 | 9:00 | 12:00 |  | Install LLT |  |  |  |  | closed | zen |  | 1 | 3 | Sweet | N | N | N
2 | 12:00 | 15:30 |  | AO bench setup and checkout |  |  |  |  | closed | zen | Setup Aerotech controller, WFSs, chopper & delay generator. | 1 | 3.5 | Roberts | N | N | N
3 | 13:30 | 17:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final adjustment and testing of laser, control loops. | 1 | 4 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
4 | 16:00 | 16:30 |  | Set up & test safety systems |  |  |  |  | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
5 | 16:30 | 17:30 |  | BTO & LLT alignment |  |  |  |  | closed | zen | Check BTO and align LLT with stimulus laser. | 1 | 1 | Bouchez | N | N | 660
6 | 17:30 | 18:30 |  | Laser/BTO/LLT integrated test |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner | [8 empty] | 1
7 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
8 | 21:00 | 22:00 |  | LGS acq. & LLT boresighting |  |  |  |  | LGS | zen | Measure LGS size & flux at zenith; adjust boresighting if needed. | 1 | 1 | Bouchez | N | N | Y
9 | 22:00 | 24:00 |  | LLT image quality |  |  |  |  | LGS | zen | Optimize LGS spot size by translating LLT secondary. | 2 | 2 | Petrie | N | N | Y
10 | 24:00 | 25:00 |  | LGS bright star optimization |  |  |  |  | LGS | V=11 | Optimize performance on a bright star; measure Strehl. | 1 | 1 | Bouchez | Y | Y | Y
11 | 25:00 | 26:30 |  | Circular polarization exp. |  |  |  |  | LGS | zen | Repeat Jul. 06 experiment. Requires person at prime focus. | 2 | 1.5 | Bouchez | Y | N | Y
12 | 26:30 | 28:00 |  | LGS science demo |  |  |  |  | LGS | V=15 | Observe 1 science target. | 2 | 1.5 | Bouchez | Y | Y | Y
13 | 28:00 | 29:00 |  | LOWFS vignetting |  |  |  |  | NGS | V=10 | Check vignetting on LOWFS at various positions in patrol field. | 2 | 1 | Roberts | N | N | N
2007-07-25 |  |  |  | 20:01 | 20:54 | 20:27 | 4:54 | 5:47
1 | 15:30 | 17:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Check laser power, wavefront quality, frequency lock. | 1 | 2 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
2 | 16:00 | 16:30 |  | Set up & test safety systems |  |  |  |  | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
3 | 16:30 | 17:30 |  | BTO & LLT alignment |  |  |  |  | closed | zen | Check BTO and align LLT with stimulus laser. | 1 | 1 | Bouchez | N | N | 660
4 | 17:30 | 18:30 |  | Laser/BTO/LLT integrated test |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner | [8 empty] | 1
5 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
6 | 21:00 | 22:00 |  | LGS acquisition & checkout |  |  |  |  | LGS | V=11 | Measure LGS size & flux at zenith; performance on V=11 NGS. | 1 | 1 | Roberts | Y | N | Y
7 | 22:00 | 28:00 |  | LGS science demo |  |  |  |  | LGS | V=16 | Observe 3 science targets. | 2 | 6 | Bouchez | Y | Y | Y
8 | 28:00 | 29:00 |  | Isoplanatic angle |  |  |  |  | LGS | V=15 | Compare LGS & NGS isoplanatic angle. | 3 | 1 | Bouchez | Y | Y | Y
2007-07-26 |  |  |  | 20:00 | 20:53 | 20:31 | 4:55 | 5:48
1 | 15:30 | 17:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Check laser power, wavefront quality, frequency lock. | 1 | 2 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
2 | 16:00 | 16:30 |  | Set up & test safety systems |  |  |  |  | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
3 | 16:30 | 17:30 |  | BTO & LLT alignment |  |  |  |  | closed | zen | Check BTO and align LLT with stimulus laser. | 1 | 1 | Bouchez | N | N | 660
4 | 17:30 | 18:30 |  | Laser/BTO/LLT integrated test |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner | [8 empty] | 1
5 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
6 | 21:00 | 22:00 |  | LGS acquisition & checkout |  |  |  |  | LGS | V=11 | Measure LGS size & flux at zenith; performance on V=11 NGS. | 1 | 1 | Roberts | Y | N | Y
7 | 22:00 | 29:00 |  | Shared-risk Science |  |  |  |  | LGS | V=17 | LGS-AO Multiplicity and Planet Formation at Bottom of IMF | 1 | 7 | Kulkarni | Y | N | Y
2007-07-27 |  |  |  | 19:59 | 20:52 | 20:35 | 4:56 | 5:49
1 | 15:30 | 17:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Check laser power, wavefront quality, frequency lock. | 1 | 2 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
2 | 16:00 | 16:30 |  | Set up & test safety systems |  |  |  |  | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
3 | 16:30 | 17:30 |  | BTO & LLT alignment |  |  |  |  | closed | zen | Check BTO and align LLT with stimulus laser. | 1 | 1 | Bouchez | N | N | 660
4 | 17:30 | 18:30 |  | Laser/BTO/LLT integrated test |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner | [8 empty] | 1
5 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
6 | 21:00 | 22:00 |  | LGS acquisition & checkout |  |  |  |  | LGS | V=11 | Measure LGS size & flux at zenith; performance on V=11 NGS. | 1 | 1 | Bouchez | Y | N | Y
7 | 22:00 | 29:00 |  | Shared-risk Science |  |  |  |  | LGS | V=17 | LGS-AO Multiplicity and Planet Formation at Bottom of IMF | 1 | 7 | Lloyd | Y | N | Y
2007-07-28 |  |  |  | 19:59 | 20:51 | 20:39 | 4:57 | 5:49
1 | 15:30 | 17:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Check laser power, wavefront quality, frequency lock. | 1 | 2 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
2 | 16:00 | 16:30 |  | Set up & test safety systems |  |  |  |  | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
3 | 16:30 | 17:30 |  | BTO & LLT alignment |  |  |  |  | closed | zen | Check BTO and align LLT with stimulus laser. | 1 | 1 | Bouchez | N | N | 660
4 | 17:30 | 18:30 |  | Laser/BTO/LLT integrated test |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner | [8 empty] | 1
5 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
6 | 21:00 | 22:00 |  | LGS acquisition & checkout |  |  |  |  | LGS | V=11 | Measure LGS size & flux at zenith; performance on V=11 NGS. | 1 | 1 | Bouchez | Y | N | Y
7 | 22:00 | 29:00 |  | Shared-risk Science |  |  |  |  | LGS | V=17 | LGS-AO Multiplicity and Planet Formation at Bottom of IMF | 1 | 7 | Lloyd | Y | N | Y