## Test schedule
Palomar LGSAO test schedule | [10 empty] | v1.2: 08/20/07 - AB & JR
23-25 August 2007 (local) | [10 empty] | Spotters requested 1930 - 05:30 PDT (on station 20:15 - 05:20)
Test ID | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description | Priority | Duration | Lead | Clear sky | r0>10cm | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2007-08-23 |  |  |  | 19:33 | 20:22 | 22:21 | 5:19 | 6:08
1 | 9:00 | 13:00 |  | Install LLT |  |  |  |  | closed | zen |  | 1 | 4 | Sweet | N | N | N
2 | 13:00 | 16:00 |  | AO bench setup and checkout |  |  |  |  | closed | zen | Check DAD, WFSs, chopper & delay generator. | 1 | 3 | Roberts | N | N | N
3 | 13:30 | 17:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Final adjustment and testing of laser, control loops. | 1 | 4 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
4 | 16:00 | 16:30 |  | Set up & test safety systems |  |  |  |  | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
5 | 16:30 | 17:30 |  | BTO & LLT alignment |  |  |  |  | closed | zen | Check BTO and align LLT with stimulus laser. | 1 | 1 | Roberts | N | N | 660
6 | 17:30 | 18:30 |  | Laser/BTO/LLT integrated test |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner | [8 empty] | 1
7 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
8 | 20:30 | 21:30 |  | LGS acq. & LLT boresighting |  |  |  |  | LGS | zen | Measure LGS size & flux at zenith; adjust boresighting if needed. | 1 | 1 | Bouchez | N | N | Y
9 | 21:30 | 23:30 |  | LLT image quality |  |  |  |  | LGS | V=3 | Compare LLT NGS imaging and LGS image quality | 3 | 2 | Bouchez | N | Y | Y
10 | 23:30 | 25:00 |  | Circular polarization exp. |  |  |  |  | LGS | zen | Repeat Jul. 06 exp. Requires person at PF. V filter on Acq. | 2 | 1.5 | Bouchez | Y | N | Y
11 | 25:00 | 29:00 |  | LOWFS performance |  |  |  |  | LGS | V=17 | Observe LGS targets with V=11,15,16,17,18 tip/tilt stars | 2 | 4 | Roberts | Y | Y | Y
12 | 29:00 | 29:30 |  | LOWFS vignetting |  |  |  |  | NGS | V=10 | Take final few data points | 3 | 0.5 | Roberts | N | N | N
2007-08-24 |  |  |  | 19:31 | 20:20 | 22:25 | 5:20 | 6:09
1 | 15:30 | 17:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Check laser power, wavefront quality, frequency lock. | 1 | 2 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
2 | 16:00 | 16:30 |  | Set up & test safety systems |  |  |  |  | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
3 | 16:30 | 17:30 |  | BTO & LLT alignment |  |  |  |  | closed | zen | Check BTO and align LLT with stimulus laser. | 1 | 1 | Bouchez | N | N | 660
4 | 17:30 | 18:30 |  | Laser/BTO/LLT integrated test |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner | [8 empty] | 1
5 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
6 | 20:30 | 21:30 |  | LGS acquisition & checkout |  |  |  |  | LGS | V=11 | Measure LGS size & flux at zenith; performance on V=11 NGS. | 1 | 1 | Roberts | Y | N | Y
7 | 21:30 | 23:00 |  | Isoplanatic angle |  |  |  |  | LGS | V=15 | Measure LGS & NGS isoplanatic angle. | 3 | 1.5 | Bouchez | Y | Y | Y
8 | 23:00 | 29:30 |  | LGS science demo |  |  |  |  | LGS | V=16 | Observe science targets. | 2 | 6.5 | Cameron | Y | Y | Y
2007-08-25 |  |  |  | 19:30 | 20:19 | 22:29 | 5:21 | 6:09
1 | 15:30 | 17:30 |  | Prepare laser for observing |  |  |  |  | closed | NA | Check laser power, wavefront quality, frequency lock. | 1 | 2 | Tripathi | N | N | N
| 15:30 | 16:00 |  | status and safety meeting | [8 empty] | 0.5
2 | 16:00 | 16:30 |  | Set up & test safety systems |  |  |  |  | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
3 | 16:30 | 17:30 |  | BTO & LLT alignment |  |  |  |  | closed | zen | Check BTO and align LLT with stimulus laser. | 1 | 1 | Bouchez | N | N | 660
4 | 17:30 | 18:30 |  | Laser/BTO/LLT integrated test |  |  |  |  | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner | [8 empty] | 1
5 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
6 | 20:30 | 21:30 |  | LGS acquisition & checkout |  |  |  |  | LGS | V=11 | Measure LGS size & flux at zenith; performance on V=11 NGS. | 1 | 1 | Roberts | Y | N | Y
7 | 21:30 | 29:30 |  | Shared-risk Science |  |  |  |  | LGS | V=17 | LGS-AO Multiplicity and Planet Formation at Bottom of IMF | 1 | 8 | Cameron | Y | N | Y