## Test schedule
Palomar LGSAO test schedule | [6 empty] | v1.0: 08/05/08 - AB
11-13 August 2008 (local) | [6 empty] | Spotters requested 18:30/19:30 - 05:15 PDT (on station 20:30 - 05:15)
Test ID | PDT start | PDT end | stat | Test Name | Obs mode | Target | Description | Priority | Duration | Lead | Clear sky | r0>10cm | Laser
2008-08-11
1 | 8:00 | 11:00 |  | Install AO | closed | zen |  | 1 | 3 | Pal | N | N | N
2 | 11:00 | 13:00 |  | Install LLT | closed | zen |  | 1 | 2 | Pal | N | N | N
3 | 11:00 | 15:30 |  | AO bench setup | closed | zen | Check WFS focus, LOWFS acq., chopper & delay generator. | 1 | 4.5 | Roberts | N | N | N
4 | 12:00 | 15:30 |  | Prepare laser | closed | NA | Verify laser power, stability, wavefront, frequency lock. | 1 | 3.5 | Velur | N | N | N
| 15:30 | 16:00 |  | status and safety meeting |  |  |  |  | 0.5
5 | 16:00 | 16:30 |  | Set up & test safety systems | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
6 | 16:00 | 18:00 |  | Optimize PHARO | closed | zen | Optimize PHARO focus, pupil, centroid offsets. | 1 | 2 | Hickey | N | N | N
7 | 16:30 | 17:30 |  | BTO & LLT alignment | closed | zen | Check BTO and align LLT with stimulus laser. | 1 | 1 | Bouchez | N | N | 660
8 | 17:30 | 18:30 |  | Laser/BTO/LLT integrated test | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner |  |  |  |  | 1
9 | 20:00 | 20:30 |  | NGS Checkout | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
10 | 20:30 | 22:30 |  | LGS acquisition | LGS | zen | Acquire LGS, focus LLT, measure LGS FWHM. Boresight LLT if needed. | 1 | 2 | Bouchez | N | N | Y
11 | 22:30 | 24:30 |  | LGS photometry | LGS | zen | Adjust 1/4-wave plate. Measure LGS return and calibrate. | 1 | 2 | Bouchez | Y | N | Y
12 | 24:30 | 25:00 |  | ACAM LGS platescale | LGS | V=11 | Measure acquisition camera LGS platescale. | 2 | 0.5 | Bouchez | Y | N | Y
13 | 25:00 | 27:00 |  | LGS bright-star performance | LGS | V=11 | Optimize performance with bright NGS. | 1 | 2 | Bouchez | Y | N | Y
14 | 27:00 | 29:00 |  | LOWFS performance | LGS | V=17 | Optimize and measure performance with V=15,16,17 NGS. | 2 | 2 | Roberts | Y | Y | Y
2008-08-12
1 | 12:00 | 15:30 |  | Prepare laser | closed | NA | Verify laser power, stability, wavefront, frequency lock. | 1 | 3.5 | Velur | N | N | N
| 15:30 | 16:00 |  | status and safety meeting |  |  |  |  | 0.5
2 | 16:00 | 16:30 |  | Set up & test safety systems | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
3 | 16:30 | 17:30 |  | Laser/BTO/LLT integrated test | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner |  |  |  |  | 1
4 | 20:00 | 20:30 |  | NGS Checkout | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
5 | 20:30 | 22:00 |  | LGS acquisition & checkout | NGS | V=11 | Measure LGS size & flux at zenith; performance on V=11 NGS. | 1 | 1.5 | Bouchez | Y | N | Y
6 | 22:00 | 24:00 |  | Performance vs. Elevation | LGS | V=11 | Acquire 5 stars, 45-90 deg. Elevation | 1 | 2 | Bouchez | Y | N | Y
7 | 24:00 | 29:00 |  | LGS science demo | LGS | V=16 | Observe science targets. | 2 | 5 | Dekany | Y | Y | Y
2008-08-13
1 | 12:00 | 15:30 |  | Prepare laser | closed | NA | Verify laser power, stability, wavefront, frequency lock. | 1 | 3.5 | Velur | N | N | N
| 15:30 | 16:00 |  | status and safety meeting |  |  |  |  | 0.5
2 | 16:00 | 16:30 |  | Set up & test safety systems | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
3 | 16:30 | 17:30 |  | Laser/BTO/LLT integrated test | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner |  |  |  |  | 1
4 | 20:00 | 20:30 |  | NGS Checkout | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
5 | 20:30 | 22:00 |  | LGS acquisition & checkout | NGS | V=11 | Measure LGS size & flux at zenith; performance on V=11 NGS. | 1 | 1.5 | Bouchez | Y | N | Y
6 | 22:00 | 29:00 |  | LGS science demo | LGS | V=16 | Observe science targets. | 2 | 7 | Dekany | Y | Y | Y