## Test schedule
Palomar LGSAO test schedule | [6 empty] | v3: 08/12/08 - AB
11-13 August 2008 (local) | [6 empty] | Spotters requested 18:30/19:30 - 05:15 PDT (on station 20:30 - 05:15)
Test ID | PDT start | PDT end | stat | Test Name | Obs mode | Target | Description | Priority | Duration | Lead | Clear sky | r0>10cm | Laser
2008-08-12
1 | 14:30 | 15:30 |  | Prepare laser | closed | NA | Verify laser power, stability, wavefront, frequency lock. | 1 | 1 | Velur | N | N | N
| 15:30 | 16:00 |  | status and safety meeting |  |  |  |  | 0.5
2 | 16:00 | 16:30 |  | Set up & test safety systems | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
3 | 40:00 | 41:30 |  | AO pupil stability | closed | slew | Investigate pupil stability vs. pointing. Need telescope operator. | 2 | 1.5 | Roberts | N | N | N
4 | 65:30 | 66:30 |  | Laser/BTO/LLT integrated test | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner |  |  |  |  | 1
5 | 20:00 | 20:30 |  | NGS Checkout | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
6 | 20:30 | 22:30 |  | LGS acquisition | LGS | zen | Acquire LGS, focus LLT, measure LGS FWHM. Boresight LLT if needed. | 1 | 2 | Bouchez | N | N | Y
7 | 22:30 | 23:30 |  | LGS photometry | LGS | zen | Adjust 1/4-wave plate. Measure LGS return and calibrate. | 1 | 1 | Bouchez | Y | N | Y
8 | 23:30 | 23:45 |  | ACAM LGS platescale | LGS | V=11 | Measure acquisition camera LGS platescale. | 2 | 0.25 | Bouchez | Y | N | Y
9 | 23:45 | 24:45 |  | LGS bright-star performance | LGS | V=11 | Optimize performance with bright NGS. | 1 | 1 | Roberts | Y | N | Y
10 | 24:45 | 26:45 |  | LGS vs. Elevation | LGS | V=11 | Acquire 8 targets, 45-90 deg elev. Measure LGS FWHM, flux. | 1 | 2 | Bouchez | Y | N | Y
11 | 26:45 | 28:45 |  | SWIFT performance | LGS | V=15 | Measure PSF vs. wavelength for SWIFT observing scenarios | 2 | 2 | Bouchez | Y | Y | Y
2008-08-13
1 | 12:00 | 15:30 |  | Prepare laser | closed | NA | Verify laser power, stability, wavefront, frequency lock. | 1 | 3.5 | Bouchez | N | N | N
| 15:30 | 16:00 |  | status and safety meeting |  |  |  |  | 0.5
2 | 16:00 | 16:30 |  | Set up & test safety systems | closed | NA | Install hazard signs, barriers and test interlocks. | 1 | 0.5 | Cromer | N | N | N
3 | 16:30 | 17:30 |  | Laser/BTO/LLT integrated test | closed | zen | Verify laser alignment to BTO in Coude, Dome, LLT. | 1 | 1 | Bouchez | N | N | Y
| 18:30 | 19:30 |  | dinner |  |  |  |  | 1
4 | 20:00 | 20:30 |  | NGS Checkout | NGS | V=8 | Measure seeing, NGS performance. | 1 | 0.5 | Hickey | N | N | N
5 | 20:30 | 22:00 |  | LGS acquisition & checkout | NGS | V=11 | Measure LGS size & flux at zenith; performance on V=11 NGS. | 1 | 1.5 | Bouchez | Y | N | Y
6 | 22:00 | 29:00 |  | LGS science demo | LGS | V=16 | Observe science targets. | 2 | 7 | Dekany | Y | Y | Y