## Sheet1
√ | T-Time | local time | Action | Notes
~ PT
| 10 h | 18:30 | Begin comm.: update on Centaur, S/S-C stack status & position, expected separation time, expected impact time & location.
| ~9 h 30 m | 18:50 | Confirm Centaur separation, update on Centaur & S-S/C status. | Can confirm successful separation via telemetry & visual confirmation from spacecraft cameras.
| 9 h | 19:30 | Hourly update re. Centaur & S-S/C position, status, payload ops and data return, expected impact location & time.
| 8 h | 20:30 | Hourly update re. Centaur & S-S/C position, status, payload ops and data return, expected impact location & time. | Note no T-7hr, T-6hr updates: SOC on break.
| 5 h | 23:30 | Hourly update re. Centaur & S-S/C position, status, payload ops and data return, expected impact location & time.
| 4 h | 0:30 | Hourly update re. Centaur & S-S/C position, status, payload ops and data return, expected impact location & time.
| ~3.5 h | 1:00 | Approx. time of CAM, Jen to attend CAM to obtain updated impact times & coordinates. | CAM=Command Approval Meeting. At CAM will receive most updated impact time, location info.
| ~3 h | ~1:30:00 AM | Report on final update for impact coordinates and times from CAM. | Jen will provide updated coordinates and impact times as soon as CAM is complete.
| 2 h | 2:30 | Hourly update re. Centaur & S-S/C position, status, payload ops and data return, expected impact location & time.
| 2 h | 2:30 | Poll Astronomers – who is online, weather, conditions, etc.
| 1 h | 3:30 | Hourly update re. Centaur & S-S/C position, status, payload ops and data return, expected impact location & time.
| ~50 m | 3:40 | Spacecraft payload on, indicate are streaming data online
| 50 m | 3:40 | Updates every 10 minutes regarding Centaur & S/S-C position, status, payload ops & data return expected impact location & time.
| 40 m | 3:50 | Updates every 10 minutes regarding Centaur & S/S-C position, status, payload ops & data return expected impact location & time.
| 30 m | 4:00 | Updates every 10 minutes regarding Centaur & S/S-C position, status, payload ops & data return expected impact location & time.
| 30 m | 4:00 | POLL Astronomers - on target, pointing nominal.
| 20 m | 4:10 | Updates every 10 minutes regarding Centaur & S/S-C position, status, payload ops & data return expected impact location & time.
| 10 m | 4:20 | Updates every 10 minutes regarding Centaur & S/S-C position, status, payload ops & data return expected impact location & time.
| 9 m | 4:21 | Updates every minute regarding Centaur & S/S-C position, status, expected impact location & time.
| 8 m | 4:22 | Updates every minute regarding Centaur & S/S-C position, status, expected impact location & time.
| 7 m | 4:23 | Updates every minute regarding Centaur & S/S-C position, status, expected impact location & time.
| 6 m | 4:24 | Updates every minute regarding Centaur & S/S-C position, status, expected impact location & time.
| 5 m | 4:25 | Updates every minute regarding Centaur & S/S-C position, status, expected impact location & time.
| 4 m | 4:26 | Updates every minute regarding Centaur & S/S-C position, status, expected impact location & time.
| 3 m | 4:27 | Updates every minute regarding Centaur & S/S-C position, status, expected impact location & time.
| 2 m |  | Updates every minute regarding Centaur & S/S-C position, status, expected impact location & time.
| 1 m | 4:29 | Updates every minute regarding Centaur & S/S-C position, status, expected impact location & time.
| 1 m -0 |  | Continuous updates regarding Centaur & S/S-C.
| 0 | 4:32 | CONFIRM IMPACT. Indicate impact location. | Impact location to be confirmed wrt pre-determined grid provided to teams.
| 0 - 4 m |  | Real-time info re. S-S/C data
| 4 m | 4:36 | Confirmation of S-S/C impact. | To be confirmed via loss of S/C telemetry.
| T+10 mins | 4:44 | POLL for observatory status to support Tony T+30 minute statement
| T+ 0-1 hour |  | Astronomer submission of obs. info, visuals to support T+2 hour press conference | Data & info shared via FTP site; may need correspondence from Jen if more info/clarification needed re. data to support press conference.
| T+1 hour | 5:30:00-6:00 AM | Jen submits visuals to PAO for inclusion in press conference.
| T+2 hour | 7:00 | Press conference.