## Slide 1: ZTF Technical Status
Nov 30, 2016
Roger Smith

## Slide 2: Exploded view of cryostat

## Slide 3: Milestones
CRYOSTAT:
Assembly fixtures: story boards developed; fixtures successful
Dewar assembled: low outgassing, no leaks
Window installed: survives pressure.
Window heater: heating works; throughput and reflectivity good.
All CCDs installed with field flatteners: no fit or ESD problems
Cooling system in test: power curves optimized; adequate margin, but flexible links need tuning.
CCD controllers: exhaustive tests automated; tests completed.
CCD Waveform Definitions: done; better tools developed for this.
CCD testing: In progress … all CCD outputs working. Reading out.

## Slide 4: Milestones
TELESCOPE
Dome drive: new speed controlled motor & gearbox
Telescope drives: new motors and electronics in use with PTF.
Bonn/DESY shutter: installed and working on PTF
Trim plate: cell design, with seals and drain for washing
Forward Baffle: new; less scattered light
Spiders, hub: designed (fabrication about to start).
Filter exchanger: designed; in fabrication

## Slide 5: Milestones
OBSERVATORY
HVAC & electrical: upgraded
Air conditioned equipment room: added to exterior
Dry air system: higher volume system installed
Wind screen: refurbished (but still not automated)
Downlink: data rate improved to meet requirements.

## Slide 6: In progress or pending
CCD testing and optimization
CCD readout software
System software
On-telescope Electronics rack
  Water cooling under test
  Assembly in progress
Spider and hub fabrication
Flat field illuminator
Trim plate polishing and coating
Dome Control Software: upgrade algorithm.
Lightning: protection
New Telescope Control Software
Wind screen: automation

## Slide 7: Focal plane cold and operating
2 layer AR coating
Single layer AR coating
Delta doped, multi-layer AR coating, fully depleted thick CCDs

## Slide 8: ITO window heater
+ 68.5
CCDs cold, ~20W heat
Only 1 C gradient,
Power as expected
CCDs warm

## Slide 9: Assembly story boards

## Slide 10: Field flattener installation on CCD

## Slide 13: Guider part way into its housing

## Slide 24: JT Cooler test system

## Slide 25: Cooling power measured at Caltech

## Slide 26: Cooling system works
Need new thermal links to bring CCD temperatures down to 155 K with no heater

## Slide 27: Thermal links and getters
These need to be replaced with more conductive links 

## Slide 28: CCDs outputs all alive
All CCDs are reading out.
Overscan and prescan in parallel and serial directions is present.
Cosmic rays are present.
Still much work to be done.

## Slide 29: Video Signal (slowed for clarity)
Positive
Video Output
Inverted
Reference
Differential
Video Output
Reduced feedthrough
Faster settling
Noise immunity

## Slide 30: Automated Testing Data
With 72 total video channels, test automation is essential. E.g…
 Feedthrough pulse height vs RG_low level for 64 channels:
 Data acquired and analyzed automatically in ~15 minutes.

## Slide 31
Dec 2015
Stephen Kaye, EE
Peter Mao, Physicist
STA Archon CCD controllers
One per quadrant, one for guide/focus

## Slide 32: Automated Test Example
 Response on each channel versus the other 15. (one of 5 controllers)
Large data set taken and analyzed without interaction.
Controller-only crosstalk test

## Slide 33: Waveform Definition Language (WDL)
Developed “compiler” for language that waveforms and sequences to be defined by timing rules.
Timing and voltages can be parameterized.
Parameter can then be manipulated by scripts which automate tests.
Can support many permutations of variable clock levels, shifting direction, and waveform timing.
Can implement dependencies of one bias voltage on another etc.

## Slide 34: Robot for filter exchanger
Michael Porter, ME:
Filter Exchanger design
Jake Zimmer,
Intern: magnetic latch sensing
Kuka Robot

## Slide 35: Full P48 solid model

## Slide 36: Cutaway (spiders suppressed)
CCD controllers outside end of spiders
Filter storage closet docks through manhole
Bonn Shutter
New forward baffle
Filter filter exchange robot

## Slide 37: Filter deployment
Redundant latching mechanisms, fully captive at all times

## Slide 38
Robot retracts and parks under ring girder so no additional beam obstruction
Only 23% beam obstruction by instrument + spiders
Cables and refrigerant lines hidden inside spiders.

## Slide 39: Forward baffle

## Slide 40: Bonn Shutter on dome floor

## Slide 41: Modest increase in area presented to wind

## Slide 42: Flat field illuminator
Moving into position
Almost light tight when aligned: ~2” gap with soft gaskets
Ring of LEDs in various colors mounted to illuminator baffle, not telescope.
Fine encoder over short distance around dome docking location allows telescope to move to actual dome position, so dome positioning not critical.
In position

## Slide 43: Data link rate monitoring

## Slide 44: Good weather

## Slide 45: High humidity

## Slide 46: ZTF focal plane last night