## Sheet1
| ADC Module Noise | ADC DNL | ADC crosstalk | Clock driver noise | Clock driver range | Clock linearity | Bias noise | Bias linearity
notes: | use clamped/shorted version |  |  |  |  | requires attenuator | essentially the same as the clock driver noise test but w/ different input | requires attenuator
manual connections | Done | Done | Done | Done | Done
manual execution (archongui) | Done | Done | Done | Done | Done
automated connection | Done | Done | Done | Done | Done | Done | Done | Done
semi automated execution (ztftest) | Done (ACF/ZTFtest) | Done (ACF/ZTFtest) | Done (ACF/ZTFtest) | pre-empted by full automation
fully automated execution (general python script | Done | Done | Limited by VICD issues | Done | Done | Done | Req TB2 or TB3 | Req TB2 or TB3
data products defined | Done | Done | Done | Done | Done | Done | Done | TBD
manual analysis | Done | Done | Done | Done | Done |  | Done (use clock noise)
analysis scripts ready | Done | Done | Done | Done | Done | Done | TBD | TBD
analysis products defined | Done | Done | Done | Done | Done | Done | TBD | TBD
Verifications
controller 0 | Done | Done - adc1 a bit funky | Done | Done | Done | Done
controller 1 | Done | Done | Done | Done | Done | Done
controller 2 | Done | Done | Done Driver 9 bad at BP | Done | Done | Done
controller 3 | Done | Done | Done | Done | Done | Done
controller 4 | Done | Done | Done | Done | Done | Done
Key | Done | Task has been completed
| Req X | Task requires additional hardware
| in progress | Task in progress
| TBD | Task not started yet | gg
| TBD | Task not started, expendable