## Slide 1: ZTF Observatory Schedule Review February 22, 2017
Goals:
Review the proposed ZTF-P48 changeover schedule;
  Confirm proposed timing meets the expected project plan goals;
  Confirm timing of activities that require campus & summit coordination;
  Adjust phasing and duration of activities;
Identify items that pose a potential risk to the proposed schedule;
.

## Slide 2: Milestones
End of iPTF science operations : February 28, 2017
ZTF changeover begins at P48: March 1, 2017
Camera Alignment Testing (early): May 2 – 11, 2017
Camera Alignment Testing (baseline): May 23 – June 6, 2017
Trim plate est. at Palomar (soonest): July 17, 2017
ZTF 1st Light: August 1, 2017
ZTF Science Verification Tests begins: September 13, 2017

## Slide 3: Commissioning Schedule drivers
Before ZTF camera alignment tests:
  Telescope structural changes;
    Access hatch enlargement & Cable ports;
    Mounting for Filter Exchanger, Instr. Support, E-Rack,
  TCS testing;
  Cable/hose mgt and air treatment system;
  Telescope interior cleaning & painting;
  Optics: primary mirror recoating & doublet corrector refurbishment;
After ZTF camera alignment test to 1st Light:
  ZTF camera CCD alignment and thermal mgt modifications; (Est 10 weeks)
  Trim plate delivery; (earliest estimates @ July 17)

## Slide 4
Week 1 - 2

## Slide 5
Week 3 - 4

## Slide 6
Week 5 – 6

## Slide 7
Week 7 – 8

## Slide 8
Week 9 – 10

## Slide 9
Detailed Work Plan
Each line item on schedule will be detailed with respect to:
  Procedure;
  Material;
  Equipment;
This will be transferred into a daily work schedule with personnel assignments;
Progress will be reported weekly during the changeover work;
Forecast to be given at least 2 weeks in advance for milestones where campus involvement will be required.

## Slide 10: Schedule Risks
Planned & Unplanned, Non-ZTF related Observatory events
  The same Palomar staff that will be working the ZTF changeover, are responsible for maintaining & fixing all other observatory systems, and supporting other project/customers;
  Other work may pull resources away from ZTF work at various times throughout the commissioning period.
  Risk Mitigation
  Maintain a reasonable contingency in the schedule;

## Slide 11: Schedule Risks
Air treatment system
  Compressor/dryer installed and operating;
  Pressure & temperature regulation system needs development;
  Risk Mitigation
  Pressure/temperature regulation can be developed without interfering with other commissioning work and is not needed until end of commissioning
Hose & cable routing/mgt
  Needs development;
  Risk Mitigation
  Campus engineering assigned to support;
  Final routing system not needed until end of commissioning;

## Slide 12: Schedule Risks
TSC development completed so far
  New Delta Tau based TCS hardware and interface cabling assembled;
  Individual sub-system functions have been bench tested;
  User interface software: Console, GXN interfaces implemented.
TCS work to be completed
  Demonstration of connection/feedback of all "housekeeping" interfaces.
  Demonstration of Delta Tau basic functionality with all observatory interfaces;
  Motion control performance tuning of all drives;
Risk Mitigation
  Define several TCS testing periods interspersed in schedule;
    4 events; 12 days;
  Alignment test can proceed using Vertex controls with manual target acquisition;
  Acquire consulting support for performance tuning phase; (Delta Tau or others)