## H2RG mounting
WIRC-POL upgrade, mechanical
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | Week of | [15 empty] | WIRC open for modification
[6 empty] | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb
[6 empty] | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
Week number
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
WIRC-POL Mechanical upgrades | 0 | 0 | 0 | 0 | 0%
H2RG mounting | 0 | 0 | 0 | 0 | 0%
Design | 7 | 10 | 0 | 0 | 0%
Molybdenum mounting block | 9 | 4 | 0 | 0 | 0%
Thermal link | 9 | 3 | 0 | 0 | 0%
Electronics mounting8 | 10 | 3 | 0 | 0 | 0%
Cable routing | 12 | 4 | 0 | 0 | 0%
Dewar interface | 14 | 4 | 0 | 0 | 0%
Procurement | 0 | 0 | 0 | 0 | 0%
Connectors (HIROSE w/ ext. flex) | 18 | 8 | 0 | 0 | 0%
Materials and consumables | 19 | 3 | 0 | 0 | 0%
WIRC inspection/design update | 26 | 3 | 0 | 0 | 0%
Fabrication | 27 | 6 | 0 | 0 | 0%
mounting block | 27 | 4 | 0 | 0 | 0%
cable build-up | 28 | 2 | 0 | 0 | 0%
interfaces | 28 | 5 | 0 | 0 | 0%
optics stack | 28 | 3 | 0 | 0 | 0%
heat shield | 29 | 3 | 0 | 0 | 0%
dewar flange | 29 | 3 | 0 | 0 | 0%
Testing (pre-installation) | 30 | 3 | 0 | 0 | 0%
Intstallation | 32 | 4 | 0 | 0 | 0%
Testing (post-installation) | 36 | 3 | 0 | 0 | 0%
*Contingency based on possible use of sidecar eelctronics

## Filter wheel mechanism
WIRC-POL upgrade, mechanical
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | Week of | [15 empty] | WIRC open for modification
[6 empty] | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb
[6 empty] | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
Week number
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
WIRC-POL Mechanical upgrades | 0 | 0 | 0 | 0 | 0%
Filterwheel mechanism | 0 | 0 | 0 | 0 | 0%
Design | 1 | 9 | 0 | 0 | 0%
gear reducer | 2 | 3 | 0 | 0 | 0%
limt switch mount/actuator | 2 | 2 | 0 | 0 | 0%
QWP/DWP mounting ring | 3 | 3 | 0 | 0 | 0%
Grism mounting ring | 3 | 4 | 0 | 0 | 0%
gear drive/motor mount | 5 | 3 | 0 | 0 | 0%
Procurement | 0 | 0 | 0 | 0 | 0%
Limit switches and cabling | 5 | 3 | 0 | 0 | 0%
Materials and consumables | 5 | 3 | 0 | 0 | 0%
gear reducer | 7 | 3 | 0 | 0 | 0%
WIRC inspection/design update | 16 | 3 | 0 | 0 | 0%
Fabrication | 17 | 6 | 0 | 0 | 0%
adapter rings | 17 | 4 | 0 | 0 | 0%
cable build-up | 18 | 2 | 0 | 0 | 0%
limit switch mounts | 18 | 5 | 0 | 0 | 0%
filter wheel modification | 18 | 3 | 0 | 0 | 0%
Testing (pre-installation) | 9 | 3 | 0 | 0 | 0%
Intstallation | 22 | 4 | 0 | 0 | 0%
Testing (post-installation) | 26 | 3 | 0 | 0 | 0%

## Focal plane mask
WIRC-POL upgrade, mechanical
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | Week of | [15 empty] | WIRC open for modification
[6 empty] | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb
[6 empty] | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
Week number
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
WIRC-POL Mechanical upgrades | 0 | 0 | 0 | 0 | 0%
Filterwheel mechanism | 0 | 0 | 0 | 0 | 0%
Design | 1 | 6 | 0 | 0 | 0%
kinematic mask | 1 | 3 | 0 | 0 | 0%
modified FP housing | 2 | 3 | 0 | 0 | 0%
flipper mechanism | 3 | 2 | 0 | 0 | 0%
actuator and linkage | 4 | 3 | 0 | 0 | 0%
cabling (and possibly status/pos. sensor) | 5 | 2 | 0 | 0 | 0%
Procurement | 4 | 4 | 0 | 0 | 0%
actuator | 4 | 3 | 0 | 0 | 0%
bearings | 4 | 3 | 0 | 0 | 0%
Materials and consumables | 5 | 3 | 0 | 0 | 0%
WIRC inspection/design update | 16 | 3 | 0 | 0 | 0%
Fabrication | 17 | 6 | 0 | 0 | 0%
FP housing | 17 | 4 | 0 | 0 | 0%
flipper mechanism | 18 | 5 | 0 | 0 | 0%
collimator plate modification | 18 | 5 | 0 | 0 | 0%
mask and compliant support | 18 | 5 | 0 | 0 | 0%
Testing (pre-installation) | 22 | 1 | 0 | 0 | 0%
Intstallation | 23 | 3 | 0 | 0 | 0%
Testing (post-installation) | 26 | 3 | 0 | 0 | 0%