## actions
action | who | when | status | closure | comments
update PFI configuration with new information | braun | 2011-02-10 | closed
Provide feedback on review objectives by Thursday for first telecon | Kirk, Roger, Dave | 2011-10-13 | closed
Talk to Rick Denzin – proposal requirements for money from Caltech w/ japan as the original source | robin | 2011-10-14 | closed
Work w/ Rich on proposal preparation and identify schedule items to complete | robin | 2011-10-14 | closed
udpate review template | Robin | 2011-10-17 | closed
Comments/questions on technical design description & schedule to Mike/robin for Marseille meeting or next weeks telecon | all | 2011-10-18 | closed
pfi & positioner schedule update | robin/dave/mike | 2011-10-26 | closed
define bridge funding for JPL effort | robin | 2011-10-28 | closed | need cost inputs
proposal outline | robin | 2011-10-28 | closed |  | started w/ Mike's task plan
identify opportunities for schedule acceleration - identify 3/2014 milestones | robin | 2011-11-02 | closed | n/a
schedule feedback | dave, larry, roger, mike | 2011-11-29 | closed
comment on conceptual phase contract mod | rich | 2011-11-29 | closed | look to Japan to identify fastest path
request extended conceptual phase funding | robin | 2011-11-29 | closed | email 11/29
confirm process on request for bridge/full funding | robin | 2011-11-29 | closed | requested info email 11/29
provide list of items needed for the PFI | dave | 2011-12-01 | closed | email 11/30
submit request for requirements to the project/SE team | robin | 2011-12-01 | closed
cost inputs, preliminary | dave, larry, rich, mike | 2011-12-02 | closed
Schedule to produce review material | robin | 2011-12-05 | closed | sent out calender 'PFS Calender thru CoDR.xlsx' | udpate w/ Feb/March date
get ROM from New Scale | dave | 2012-01-17 | closed |  | discussion scheduled for 2/2
reconcile cabling costs | larry/dave/robin | 2012-01-17 | closed | written up in cost document
I&T cost estimate | rich | 2012-01-17 | closed |  | first version done. Needs more refinement
get positioner sw costs | robin | 2012-01-17 | closed
deliver/post updated SW block diagram | dekany | 2012-02-06 | closed
develop plan for having the design and analysis of the PFI structure elements started at JPL and fabrication and test done by ASIAA | bruno | 2012-02-10 | closed
solid model of the PFI allowable volume | shimono | 2012-02-10 | closed
Need to have a metrology system, preferably the metrology system, for pfi/positioned testing in Pasadena prior to delivery – include in assumptions in review package | Dave | first draft | closed
send report for first contract to IPMU (thru caltech) | robin |  | closed
request structure for design defintion documents - locations, control, owners, etc (from 7/26 se mtg) | robin | 2012-07-30 | closed |  | requested, discussions occurring
post - update and distribute PSF trade document and metrology system document | peter | 2012-07-31 | closed | posted on twiki
post on the twiki. presentation on fiber routing apporach and list interface features/requirements that are needed | roger | 2012-07-31 | closed | posted under system architecture
need LNA & project office inputs on size and interface info on strain relief box and connectors and recommendations on where these should be located | dave | 2012-08-16 | closed |  | in schedule rec/dels
post comments on Naoyuki's requirements document | all | 2012-08-03 | closed | submitted and reviewed w/ naoyuki
request instrument integration story board - (CIT-JPL provides PFI piece) | robin | 2012-08-03 | closed | requested via schedule items list to Management group
get baseline flow for microlens/fiber fabrication and integration - feeds into PFI integration storyboard | robin | 2012-08-04 | closed | requested via schedule items list to Management group
provide draft or storyboard of I&T flow - entire PFI I&T with focus on interface w/ POpt2 | dave | 2012-08-03 | closed | presented at collab mtg - posted on sumire
list deliverables for design transfer at PDR, include short description: ICDs, requirements, CAD model, prelim analysis, etc | Dave, Charlie | 2012-08-03 |  |  | part of bigger hand off/ working relationship documebt - robin
obtain the project response and request formal documentation from the SE group on the fiber routing approach | robin | 2012-08-05 | closed |  | now led by J. Gunn
include ICD PFI/fiber system in ICD list | charlie | 2012-08-10 | closed
model update | charlie | 2012-04-13 | closed
determine if the configuration can support the masking options for the PSF characterization (smith document option 3) | braun | 2012-04-15 | closed | done by asiaa
update icd list | charlie, larry | 2012-08-10 |  |  | mech section is updated
develop positioner specs for New Scale contract | Dave,Ron,Mike, charlie | 2012-07-26 | closed
review EAR guidelines | robin | 2012-07-26 | closed
Propose a test at JPL to assess the change in sky subtraction | mike | 2012-08-16 | closed | test proposed and fudning requested from Gerber
preliminary scheme for shutter | roger | 2012-08-10 |  |  | change to provide info on dots size, placement
draft approach for number, location, type of fiducial fibers | mike | 2012-08-25 | closed |  | draft out 8-23
determine if there's a requirement to be able to use the metrology system during the day | mike | 2012-08-16 | closed | mike has made a request to naoyuki that the metrology system can be used during the day
obtain the microlens system characterization/error budget to confirm mechanical approach to fiber integration and alignment and measurement | robin | 2012-08-16 | closed | requested via schedule items list to Management group
provide analysis on size and details on the dots option for the fiber mask | roger | 2012-08-29 | closed |  | just send whatever you already have
propose split on PDS system. Define needs | charlie | 2012-08-31 | closed | propose each subsystem has tehir own PDS and JPL only provides the psoitioner system
respond to ASIAA proposal on who does the power distribution system | robin | 2012-08-16 | closed |  | transferred to charlie
draft document on JPL/ASIAA work split before and after PDR (bugzilla action) | robin | 2012-08-23 |  | closed | sent out 8/23 for comments
provide example or template for SW requirements, PDR products | hrand | 2012-08-31 | closed
udpate and organize open issues list (requests to the project) | Robin | 2012-08-31 | closed
follow up on request for HSC documents - next management telecon | robin | 2012-08-31 | closed
update rec/dels for pfi & positioner | dave | 2012-08-10 | closed
Determine the sensitivity of the positioner bench – is additional cooling needed. | charlie | 2012-09-01 | closed |  | no extra cooling needed
define the raster scan calibration process to help clarify the JPL/CIT role | mike | 2012-10-29 |  |  | work w/ roger
draft document(S) that describes the software algorithms of the PFI system | peter | 2012-10-22 |  |  | list of full set of algorithms and what they do
characterize positioner tilt | joel | 2012-09-15 | closed |  | post on twiki
get info on telescope connector to instrument - Circuit data sheet with wire size, conductor count, connector type, | ron | 2012-10-29 |  |  | discussed at collab meeting - may be to PFI
throughput change with tilt, defocus | ron | 2012-09-17 | closed | post to the twiki - ron | second version to come
Rename the PFI sequencer | peter | 2012-09-19 | closed |  | from sept mmr
provide more details on fibers needed for the EM build | charlie | 2012-09-25 | closed | email sep 26, 11:54
schedule updates on V&V design thru V&V test equipment analysis, lines 175-184 on Aug 30 schedule | dan | 2012-11-02
review and update caltech rec-dels in the schedule | dan | 2012-11-02
schedule inputs for the FPGA task | larry | 2012-10-18
Decide if its useful to use the current prototype testbed software to exercise any of the production software or if it just really makes sense to wait for the EM | Peter, hrand | 2012-10-22 |  |  | from sept mmr
reconcile critical schedule items w/ schedule, update critical items. Included dels for ASIAA requested items | robin | 2012-09-26 | closed
udpate fixed fiducial fiber interace issues document | robin | 2012-09-27
get clarification on Takato's optical analysis document for comparison to Norm | mike | 2012-10-10 | closed
send model to LNA for cable wrap info after the 9/20 telecon w/ ASIAA | olivia | 2012-10-10 | closed |  | deferred to 10/22
draft procedure of removal, maintenance & repair and re-installation of Cobra positioner module needs to be followed on a story board for further discussion. | charlie | 2012-10-12 |  |  | project action item - need more info from LNA on connectors, etc
send feedback on Atsushi document | dan | 2012-10-12 | closed
provide updates on schedule issues list - more specific requests, changes to dates? | charlie/dave/olivia | 2012-10-12
Propose a transfer standard – a test that can be run often as a benchmark against an absolute measurement | mike | Dec 15 2012
schedule walk through of SW requirements | reed | 2012-10-18
produce a draft of the timing budget | peter/Mike | 2012-10-18
draft on our coordinate transformations, the IPMU coordinate transformations and how they’ll be work together | Peter | 2012-10-26