## Gen2-3
WO # | P/N | Title | Rev | Dwg Status | Fab Status | Fab Comments | Qty | Budgeted Cost | Estimate Cost | Delta | Actual Cost | Delta | Mat'l | Mass | Inspection? | Need Date | Expected Delivery | Actual Delivery | Comments
| 10354710-1 | Adapter Coupler, Cobra, Gen2 | A | Released | Delivered |  | 5 | [5 empty] | 6061-T6 |  | N | 2013-06-28 | 2013-07-31 | 2013-08-02
| 10354716-1 | Nut, Positioner, Testbed | A | Released | Delivered |  | 10 | [5 empty] | CRES 303 |  | N | 2013-06-28 | 2013-07-31
| 10354717-1 | Fin, Positioner, Testbed | B | Released | Delivered |  | 1 | [5 empty] | 6061-T6 |  | N | 2013-06-28 | 2013-07-31
| 10354718-1 | Rail, Positioner, Testbed | A | Released | Delivered |  | 1 | [5 empty] | Invar 36 |  | N | 2013-06-28 | 2013-07-31
| 10354719-1 | Plate, Torque Test | A | Released | Delivered | pins provided | 1 | [5 empty] | 6061-T6 |  | N | 2013-05-30 | 2013-07-31
| 10354720-1 | Adapter Coupler, Cobra, Test | A | Released | Delivered |  | 10 | [5 empty] | 6061-T6 |  | N | 2013-05-30 | 2013-07-31 | 2013-07-22
| 10354703-1 | Cobra Model, Stage 1 | A | Released | Delivered |  | 3 | [5 empty] | 6061-T6 |  | N
| 10354704-1 | Cobra Model, Stage 2 | A | Released | Delivered |  | 3 | [5 empty] | 6061-T6 |  | N
| 10354723-1 | Cobra Model Stage 1, GEN2 | A | Released | Delivered |  | 5 | [5 empty] | 6061-T6
| 10354712-1 | JIG, FIBER COUPLER, GEN2 | A | In Process | Not Started |  | 1 | [5 empty] | CRES 303 |  |  | ?
| 10354713-1 | JIG, FIBER ADAPTER COUPLER, GEN2 | A | In Process | Not Started |  | 1 | [5 empty] | CRES 303 |  |  | 2013-09-01 | 2013-10-01 |  | Needed these yesterday…
| 10354721-1 | FIXTURE, CHECKOUT, COBRA | A | In Process | Not Started |  | 1 | [5 empty] | 6061-T6
| 10354722-1 | FIXTURE, MOTOR MAPPING, COBRA | A | In Process | Not Started |  | 1 | [5 empty] | CRES 303
| 10354724-1 | BRACKET, TURNOVER FIXTURE | A | In Process | Not Started |  | 1 | [5 empty] | 6061-T6
| ? | EM RAIL |  | Not Started | Not Started |  | 1 | [5 empty] | INVAR-36
| ? | EM FIN |  | Not Started | Not Started |  | 1 | [5 empty] | 6061-T6
| ? | GSE COBRA RAIL COVER | A | Not Started | Not Started |  | 1 | [5 empty] | 6061-T6
| 10354705-1 | JIG, ALIGNMENT, MODULE | A | In Process | Not Started |  | 1 | [5 empty] | CRES 303
| 10354706-1 | BRACKET, JIG, ALIGNMENT | A | In Process | Not Started |  | 1 | [5 empty] | CRES 303
| ? | CAMERA BRACKET, MOTOR MAPPING |  | Not Started | Not Started |  | 1 | [5 empty] | 6061-T6

## ListData
DwgRelease | FabStatus
Not Started | Not Started
In Process | Out for Quote
Signature | In Fab
Released | Dry Film
Obsolete | Insert/Pin Install
Inspection
Ink Stamp
Paint
Delivered
Obsolete